## Instructions
ES Re-Plan Calculator Instruction
The ES Re-Plan calculator performs very much like the simple ES calculator. The instruction in blue below is taken from the ES calculator and
remains applicable. The meaning of planned duration is changed. It describes the period of execution remaining after the re-plan. The EV and
PV entries are for the remaining executable portion of the project, only.
Enter EVcum and PVcum into columns A and B of the EScalc sheet. Note that row 3 is the 1st data entry. Before each use clear all data
in columns A and B below row 2. To insure correctly calculated values, load the entire baseline (periodic values of PVcum) into column B.
Enter PV = BAC one time only. Entering PV = BAC for time periods past the planned duration (PD) will cause the message, ERROR, to
appear instead of computed values for ES, SPI(t), and SV(t). Computed values for SPI(t)mo, SPI(t)cum, SV(t)mo, and SV(t)cum are displayed
in columns I, J, L, and M, respectively.
The cumulative actual time (AT) is in reference to remaining executable portion of the project, shown in column K. The PD for the path is
calculated for the re-plan PV entries and is displayed in cell N2. In cell O2, enter the project duration up to the time of the re-plan. The ATRP
column depicts the total duration from the original project start. The forecast is displayed beneath the heading IEAC(t)RP. The forecast includes
the project duration up to the time of the re-plan. However, the indicators provide information for the project remainder and are not to be
interpreted as performance from the original project beginning.

## ES Re-Plan calc
EVcum | PVcum | # Pc=>Sc | Numerator | Denominator | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | PDRP | ATRP | IEAC(t)RP
0 | 0 | [8 empty] | 0 |  |  | 0
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
|  | Pc=>Sc | NUM | DENOM | InterpVal | EScum | ESmo | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum |  | AT-RP | IEAC(t)RP
BAC Count | 0

## Example Data
EVcum | PVcum | EVcum | PVcum |  | SPI(t)mo | SPI(t)cum | AT | SV(t)mo | SV(t)cum | PDRP | ATRP | IEAC(t)RP
93 | 93 | 93 | 93 | Compare your results obtained from using |  |  | 0 |  |  | 19 | 10
644 | 644 | 644 | 644 | this data to their corresponding values in | 0.96632 | 0.96632 | 1 | -0.033676 | -0.033676 |  | 11 | 29.6621
975 | 1710 | 975 | 1710 | columns I, J, L, M, O, P. | 0.81712 | 0.89172 | 2 | -0.18288 | -0.21656 |  | 12 | 31.3071
1275 | 2397 | 1275 | 2397 |  | 0.68191 | 0.82178 | 3 | -0.31809 | -0.53465 |  | 13 | 33.1205
1739 | 3060 | 1739 | 3060 |  | 1.0659 | 0.88281 | 4 | 0.06589 | -0.46876 |  | 14 | 31.5222
2292 | 3923 | 2292 | 3923 |  | 0.61328 | 0.8289 | 5 | -0.38672 | -0.85548 |  | 15 | 32.9218
3331 | 4722 | 3331 | 4722 |  | 0.56197 | 0.78441 | 6 | -0.43803 | -1.2935 |  | 16 | 34.2219
3869 | 5743 | 3869 | 5743 |  | 1.4844 | 0.88442 | 7 | 0.48444 | -0.80908 |  | 17 | 31.4831
4612 | 7369 | 4612 | 7369 |  | 0.28169 | 0.80908 | 8 | -0.71831 | -1.5274 |  | 18 | 33.4836
5527 | 9005 | 5527 | 9005 |  | 0.57392 | 0.78295 | 9 | -0.42608 | -1.9535 |  | 19 | 34.2673
| 10850 | Re-Plan |  |  | 0.15034 | 0.71969 | 10 | -0.84966 | -2.8031 |  | 20 | 36.4004
| 12218 |  |  |  | 0.45548 | 0.69567 | 11 | -0.54452 | -3.3477 |  | 21 | 37.3119
| 13921 | 6112 | 6325 |  | 0.39396 | 0.67053 | 12 | -0.60604 | -3.9537 |  | 22 | 38.336
| 15417 | 7432 | 7738 |  | 0.37964 | 0.64815 | 13 | -0.62036 | -4.574 |  | 23 | 39.3142
| 18170 | 8067 | 8445 |  | 0.58545 | 0.64367 | 14 | -0.41455 | -4.9886 |  | 24 | 39.5181
| 20022 | 9678 | 10766 |  | 0.98099 | 0.66616 | 15 | -0.019011 | -5.0076 |  | 25 | 38.5217
| 21936 | 11089 | 13001 |  | 1.7771 | 0.7356 | 16 | 0.77713 | -4.2305 |  | 26 | 35.8294
| 24418 | 12345 | 14295 |  | 0.91642 | 0.74623 | 17 | -0.083578 | -4.3141 |  | 27 | 35.4612
| 26186 | 14539 | 15573 |  | 0.92157 | 0.75597 | 18 | -0.078426 | -4.3925 |  | 28 | 35.1332
| 27972 | 14899 | 17808 |  | 1.3026 | 0.78474 | 19 | 0.30256 | -4.0899 |  | 29 | 34.2118
| 29397 | 15677 | 19773 |  | 1.7954 | 0.83528 | 20 | 0.79543 | -3.2945 |  | 30 | 32.747
| 30899 | 16013 | 21088 |  | 0.25113 | 0.80746 | 21 | -0.74887 | -4.0434 |  | 31 | 33.5306
| 31821 | 17031 | 22764 |  | 1.4543 | 0.83686 | 22 | 0.45432 | -3.589 |  | 32 | 32.7039
|  | 17899 | 24339 |  | 0.58904 | 0.82609 | 23 | -0.41096 | -4 |  | 33 | 33
|  | 18645 | 26310
|  | 19788 | 28012
|  | 21078 | 29113
|  | 23976 | 30008
Original |  | 25691 | 31115
|  | 27344 | 32053
|  | 29014 | 32199
30789
31067
32113
32199